## Instructions
Workbook Instructions
Fill out all applicable sections. If a cell is YELLOW, it is recommended that you enter information into that cell. If the cell is ORANGE, it is STRONGLY recommended that you enter information in that cell. If the block is white, it means some information will be transferred from a different sheet. The only exception is the Exercise Evaluation Guides (EEGs). They are intended to be printed and filled out by your Evaluators. Be sure to save your workbook any time you make an update to it!
This workbook is designed to help you plan your exercise and complete your exercise After-Action Report. It is not required that you use this specific tool.
Exercise Planning
This section describes elements and meetings to assist with the development of your exercise. Use it as a quick reference to help with planning for your exercise.
Exercise Types
This section describes the four types of discussion-based exercises and the three types of operations-based exercises. Use this section to familiarize yourself with the exercise you plan to use and ensure it is the exercise that fits your needs.
Core Capabilities
This tab contains the definitions of the FEMA Mission Areas along with the definitions of the Core Capabilities. The table is set so you can sort it by the Core Capabilities or the Mission Area. Select the dropdown arrow(s) at the top to filter alphabetically by Mission Area or Core Capability.
Notification Form
Enter your exercise information on the form.
Overview
Exercise Name | Record the exercise name in this section.
Exercise Overview | Give a brief overview of the exercise. One to two sentences to describe the exercise.
Mission Area | Use the dropdown box to select the mission area you are planning to exercise.
Core Capabilities | Use the dropdown box to select the core capability you are planning to exercise. Only those core capabilities associated with that mission area will appear in this dropdown box. Remember, every exercise tests at least one core capability; it can test more than one, but it has to test at least one. Use the other section for any additional core capability being tested.
Primary Lead Planning Organization | Record the Primary Planning Organization associated with the Exercise.
Exercise POC | Record the Primary Point of Contact for the Exercise.
Type of Exercise | Record the type of Exercise conducting. Use dropdown to select type of exercise. Refer to Exercise Types tab for information on each type of exercise to select the appropriate exercise type.
Primary Location | Record the Primary Location for the Exercise.
Date/Time | Record the Date and Time the Exercise will occur.
Invitation Only | Every Exercise will be Invitation Only.
Exercise Threat/Hazard
Use the dropdown feature and pick which applies to your scenario. If none of the list applies to your scenario, pick "Other". Then enter a description in the block and describe the scenario in the cell provided.
Planning Meeting
Click the box for each planning meeting as you complete them, and list the dates they were conducted. List the Lead Planner and the names of the members of the Planning Team.
Exercise Overview
The orange and yellow boxes need information entered into them. Some information will already be entered from previous sheets.
Exercise Name | Recorded from Notification Form.
Exercise Dates | Start date will be recorded from Notification Form. End Date needs to be entered. This is the date you plan to conduct the exercise. The first draft and final draft will auto-populate for the due date. The first draft is due 45 days after the exercise. The final drafts due 90 days after the exercise.
Scope | Will be recorded from information on the Notification Form.
Mission Area | Recorded from Notification Form.
Core Capabilities | Recorded from Notification Form.
Objectives | Record one objective for each core capability you have designated. Ensure the objectives are written in S.M.A.R.T. (Specific, Measurable, Achievable, Relevant, and Time-Bound) format. To write a S.M.A.R.T Objective, answer the following questions: Who is doing the Action? What action is being done? Where is the action being conducted? When is the action being conducted? Why is the action being conducted? During what measurable/realistic timeframe is the action being conducted?
Threat or Hazard | Recorded from Notification Form.
Scenario | Record a brief synopsis of the scenario for the exercise.
Primary Lead Planning Organization | Recorded from Notification Form.
Participating Organizations | Record all organizations participating in the exercise i.e. Agency Name (not individual names), Federal, State, Local, Tribal, etc.
Exercise POC | Recorded from Notification Form.
Contact Info | Phone number and email for the Exercise POC.
Exercise Meeting Sign-In Sheet
To be filled in by individual attending the exercise.
Primary Lead Planning Organization | Recorded from Notification Form.
Exercise Name | Recorded from Notification Form.
Type of Exercise Meeting | Use the dropdown box to select the exercise meeting you are planning to conduct.
Date | Record the date you plan to have the meeting.
Organization | Have participants record their organization.
Printed Name | Have participants record their name.
Signature | Have participants record their signature.
Email | Have participants record their email.
Exercise Evaluation Guides (EEG)
There are six EEGs that can be filled out. Each EEG will be given to an evaluator to use to evaluate the exercise. Some of this document will be filled in by previous forms. The rating is designated by the following: P Performed without challenges (4 Points) S Performed with some challenges (3 Points) M Performed with major challenges (2 Points) U Unable to be performed (1 Point) To tabulate the total score, add up the points and divide by the number of Critical Tasks. This will give the overall rating for each Capability Target. Add the rating for each Capability Target, then divide that by the number of Capability Targets. This will give you an overall rating for the core capability. When printing, ensure you print setting says "Fit ALL Columns on One Page". This will ensure the document prints correctly.
Exercise Name | Recorded from Notification Form.
Primary Lead Planning Organization | Recorded from Notification Form.
Date | Recorded from Exercise Overview Form.
Primary Location | Recorded from Notification Form.
References | List all reference documentation used to create exercise. (SOP, SOG , Plans, Procedures, Policies, etc.)
Exercise Objective | Recorded from Exercise Overview Form.
Core Capability | Recorded from Notification Form.
Capability Target | The overarching goal you are wanting to reach (Example: sheltering 200 people with in your first operational period).
Critical Task | Each individual task needed to reach the capability target. Each step in the process is an individual critical task.
Capability Target Strengths Observed | List any and all strengths identified by participants that were observed during the exercise.
Organizational Capability Target Rating | Add up the points and divide by the number of Critical Tasks. This will give the overall rating for each Capability Target. Always round down (Example: 3.9 is a 3 not a 4).
Final Core Capability Rating | Add the rating for each Capability Target, then divide that by the number of Capability Targets. This will give you an overall ratting for the core capability. Always round down (Example 3.9 is a 3 not a 4).
Evaluator Name | Record the name the Evaluator using the form.
Evaluator Email | Record the email of the Evaluator using the form.
Master Scenario Events List (MSEL)
This form will supply the injects for the exercise. This is a numerical order of how the injects will be introduced to the exercise. Inject- MSEL event introduced to a player by the control staff, representing non-playing entities, to build the exercise environment based on the exercise scenario and to drive exercise play. Contingency Inject- A MSEL event introduced to a player by the control staff when a key player expected action did not occur as planned to provide an additional opportunity to meet exercise objective. Expected Action- A MSEL event that represents an anticipated action to be taken by a player during the exercise.
Event # | The sequential number (order) the events should be introduced that follows the timeline of event /scenario.
Time | Time the inject is to be introduced to play. Either the real time the inject should be played or simulated time within the scenario (whichever you choose, be consistent through the rest of your timeline).
Event Type | What type of inject it is. Use the dropdown box to designate if an inject is a player inject, contingency inject, media inject, question for a discussion-based exercise, or other form.
Inject Mode | How the inject is delivered. Use the dropdown box to designate if the inject is given in person, radio, electronic mail, fax, satellite phone, social media, or other form.
From | Who or where the inject is coming from.
To | Who or where the inject is going to.
Inject Message / Question | For a operations-based exercise, the inject will be a message. For a discussion-based, the inject will be the question you are asking the participants.
Expected Action | What is the anticipated action to be taken by the participant or player during the exercise.
POC/Author | The point of contact or author responsible for the event. (Needed in case there is a question within the exercise that requires pausing and seeking clarification or further information.)
Core Capability | Core Capability the inject is exercising.
Comment | Additional notes or comments to support the development of the event. (Could be general information or a note for the player, the evaluator, or the person delivering the inject).
Analysis of Core Capabilities 1
Use the information gathered by your evaluator(s) on your EEG(s) during the exercise to give each objective a performance rating.
Objective | Recorded from Exercise Overview Form.
Core Capabilities | Recorded from Notification Form.
Results | Select the rating for your objective based on the assigned rating of your evaluators. P-Performed without challenges S-Performed with some challenges M-Performed with major challenges U-Unable to performed
Analysis of Core Capabilities 2
This form is to further evaluate the core capabilities. Document any strengths, Areas for Improvement, and the analysis of how the area of improvement affected the objective from being met.
Core Capability | Recorded from Notification Form.
Objective | Recorded from Exercise Overview Form.
Capability Level | Recorded from Analysis of Core Capabilities 1.
Strengths | Record three strengths observed during the exercise for each objective.
Areas For Improvement (AFI) | If the objective's Capability Level is Full, there is no areas for improvement. If the Capability Level is Patial, list any areas of improvement observed.
Analysis | Record how the area for improvement prevented the objective to be met. The analysis should describe how the area(s) for improvement prevented a full capability but should not include a corrective action. Each area for improvement corresponds to a single analysis.
Reference | Recorded from each Exercise Evaluation Guide.
Appendix A: Improvement Plan
Capability Element-POETE Planning-Development of policies, plans, procedures, mutual aid agreements, strategies, and other publications: also involves the collection and analysis of intelligence and information. Organization-Individual teams, an overall organizational structure, and leadership at each level in the structure. Equipment-Equipment, supplies, and systems that comply with relevant standards. Training-Content and methods of delivery that comply with relevant training standards. Exercises-Exercises and actual incidents that provide an opportunity to demonstrate, evaluate, and improve the ability of core capabilities to perform assigned missions and tasks to standards.
Core Capability | Recorded from Notification Form.
Issue / Area for Improvement | Recorded from Analysis of Core Capabilities 2.
Corrective Action | Record what you plan to do to improve your capabilities. This should relate to the area for improvement next to the corrective action.
Capability Element | Review the definition for POETE and record the capability element associated with the corrective action. Definition is on line 96 of this form.
Primary Responsible Organization | Record the Primary Responsible Organization for the corrective action.
Organization POC | Record the responsible party responsible for the completion of the corrective action. Ensure to record the position, not the actual person associated with the corrective action.
Start Date | Start Date will populate with the exercise start date from the Exercise Overview.
Projected Completion Date | Record a reasonable target date in the future for when you plan to have the corrective action completed and implemented.
Exercise Sign-In Sheet
To be filled in by individuals attending the exercise.
Primary Lead Planning Organization | Recorded from Notification Form.
Exercise Name | Recorded from Notification Form.
Type of Exercise | Recorded from Notification Form.
Date | Recorded the Exercise Overview Form.
Organization | Have participants record their organization.
Printed Name | Have participants record their name.
Signature | Have participants record their signature.
Email | Have participants record their email.
AAR
Insert your jurisdictions name in the the header. All other sections will be populated from information from the other forms. If there is a section not used, delete that section. Then print this form and put it with your sign in sheet. This will give you a completed AAR/IP.

## Exercise Planning
Exercise Scope
Determining the exercise scope enables planners to "right-size" an exercise to meet the objectives while staying within the resource and personnel constraints of the participation jurisdictions/organizations.
Element | Description
Exercise Type | Exercise type is based on the exercise purpose. For instance, if the intent is to review and discuss a new policy, plan, or set of procedures, a discussion-based exercise may be appropriate. If the intent is to assess the responders’ ability to implement a plan, policy, or set of procedures, an operations-based exercise may be appropriate.
Participation Level | Participation-level of jurisdictions/organizations provides information such as dates and times of participation, number of personnel involved, positions of personnel (operational, agency directors), available resources, and the intended outcomes. Participation-level limitations may include scheduling conflicts, real-world incidents, or other competing requirements. Consider simulation to alleviate the participation-level limitations. To ensure a successful exercise, the use of an Extent of Play Agreement outlines the agreement to participate.
Exercise Location | Exercise location is based on the exercise type. Discuss and decide suitable locations for the exercise to determine the scope or define artificialities required to simulate real-world incidents.
Exercise Duration | Exercise duration is based on resources and exercise objectives. When selecting the exercise duration, the planning team should determine how long the exercise will take to address the exercise objectives effectively.
Other Considerations | Other considerations may determine exercise activities that are useful to a jurisdiction/organization. Clearly defining the exercise scope early in the design process helps exercise planners keep the exercise to a manageable and realistic level.
SMART Guidelines for Exercise Objectives
Specific | Objectives should address the five W's-who, what, when, where, and why. The objective specifies what needs to be done with a timeline for completion.
Measurable | Objectives should include numeric or descriptive measures that define quantity, quality, cost, etc. Their focus should be on observable actions and outcomes.
Achievable | Objectives should be within the control, influence, and resources of exercise play and participant actions.
Relevant | Objectives should be instrumental to the mission of the organization and link to its goals or strategic intent.
Time-Bound | A specified and reasonable timeframe should be incorporated into all objectives.
Concept & Objectives (C&O) Meeting
A meeting that is the formal beginning of the exercise planning process. It is held to identify the scope and exercise objectives. For less complex exercises and for organizations with limited resources, the C&O Meeting can be conducted in conjunction with the Initial Planning Meeting (IPM).
Element | Considerations and Activities
Meeting Focus | The formal beginning of the planning process. Program priorities and objectives are determined during the C&O Meeting.
Discussion Points | • Exercise scope • Proposed objectives and aligned capabilities linked to threats and risks • Location, date, and duration • Participants and anticipated extend of play • Exercise Planning Team makeup • Assumptions and artificialities • Control and evaluation concepts • Security organizations and structure • Available resources • Logistics • Planning timeline and milestones • Local issues, concerns, and sensitivities • Re-engage with senior leaders for guidance and intent
Exercise Tools | • Meeting agenda and briefing, which includes the background and rationale for conducting the exercise.
Exercise Outcomes | • Exercise concept • Exercise timeline (group consensus) • Extent of participant play • Identification of planning team members • Planning timeline, milestones, and meeting dates
Follow-up | • Compile and distribute the C&O Meeting minutes and include the next meeting time, date, and location.
Initial Planning Meeting (IPM)
A meeting that is held to refine the scope and exercise objectives. For less complex exercises and for organizations with limited resources, the C&O Meeting can be conducted in conjunction with the IPM.
Element | Considerations and Activities
Meeting Focus | Formal beginning of the development phase. The IPM also focuses on refining the scope and the objectives for the exercise.
Discussion Points | • Clearly defined objectives and aligned capabilities linked to threats and risks • Evaluation requirements, including Exercise Evaluation Guide (EEGs) capability targets and critical tasks • Relevant plans, policies, and procedures to be evaluated • Exercise scenario • Modeling and simulation • Participants extent of play • Optimum duration of the exercise • Exercise planners' roles and responsibilities • Decision to record exercise proceedings (audio or video) • Local issues, concerns, or sensitivities • Discussion points typically covered during a C&O Meeting if one is not held • Consensus regarding the date, time, and location for next meeting • Re-engage with senior leaders to ensure alignment with guidance and intent
Exercise Tools | • Read-ahead document • Agenda material • Briefing for presenting an overview of the exercise and meeting discussion points • Threat and hazard identification assessments • Proposed room layout (discussion-based) • Map of proposed venue sites (operations-based) with description of local environment • Copy of proposed timeline and milestones for design and development • Copies of presentation briefing for meeting
Exercise Outcomes | • Any outcomes for C&O Meeting if a C&O Meeting was not conducted • Clearly defined objectives and aligned capabilities • Initial capability targets and critical tasks (reviewed and confirmed prior to the next meeting) • Scenario variables (treat, scope, venue, conditions) • List of participating organizations and extent of play • Develop exercise draft documentation (Situation Manual [SitMan], Exercise Plan [ExPlan], etc.) • Identification and availability of all source documents (plans, policies, procedures) needed for exercise documentation • Preferred communication methods among planning team • Clearly identified and assigned responsibility for logistical issues • List of tasks to be accomplished by next planning meeting, to include date and responsible planning team member • Agreed-upon date, time, and location of next planning meeting
Follow-up | • Compile and distribute the IPM meeting minutes, including the next meeting time, date, and location • Between meetings the planning team collaborates on assignments and prepares draft exercise documentation • Distribute draft documentation prior to the next scheduled meeting
Midterm Planning Meeting (MPM)
A meeting that serves as a forum to develop exercise scenario details and timeline.
Element | Considerations and Activities
Meeting Focus | The MPM is a continuation of the development phase. This meeting is primarily focused on scenario development and serves as a check-in for exercise product development.
Discussion Points | • Comments on draft exercise documentation • Construction of the scenario timeline • Development of the Master Scenario Events List (MSEL) if a MSEL meeting is not scheduled • Identification of exercise venue artificialities and/or limitations • Agreement on final logistical items • Assignment of additional responsibilities • Re-engage with senior leaders to ensure alignment with guidance and intent
Exercise Tools | • Agenda material • Briefing for presenting an overview of the exercise and meeting discussion points • IPM minutes • Draft scenario timeline • Draft documentation (Facilitator Guide, Controller/Evaluator [E/E] Handbook, etc.) • Other selected documentation needed to illustrate exercise concepts and provide planning guidance
Exercise Outcomes | • Review exercise documentation (SitMan, ExPlan, etc.) • Draft Facilitator Guide or C/E Handbook, including EEGs • Well-developed scenario to include injects (if no MSEL Meeting is scheduled) • Agreement on the exercise site • Identified logistics planning requirements • Finalization of date, time, and location on the MSEL Meeting and Final Planning Meeting (FPM)
Follow-up | • Compile and distribute the MPM meeting minutes, including the next meeting date, time, and location • Between meetings the planning team collaborates on assignments and prepares draft exercise documentation • Distribute draft documentation prior to the next scheduled meeting
Master Scenario Events List (MSEL) Meeting
A meeting for operations-based exercises that serves as a forum to build the MSEL in detail.
Element | Considerations and Activities
Meeting Focus | The MSEL meeting focuses on reviewing the timeline and developing the MSEL. Exercise planners from participating departments, agencies, jurisdictions, and organizations are included to identify activities that must occur during the exercise.
Discussion Points | • Tasks, conditions, and standards required to meet objectives • Key events and critical tasks • Event originator, target player, expected player actions, and timeframe • Contingency injects to prompt player action (if needed)
Exercise Tools | • Agenda material • Previous meeting minutes • Draft exercise documentation • Applicable plans, policies, and procedures • Agreed-upon template used to create the MSEL
Exercise Outcomes | • Key event injects and delivery timeline identified • Assignment of responsibility for conducting remaining events • Revisions of draft scenario-based documentation • Timeline for completion
Follow-up | • Compile and distribute the MSEL meeting minutes, including the next meeting date, time, and location • Between meetings the planning team collaborates on assignments and prepares draft exercise documentation • Distribute draft documentation prior to next scheduled meeting
Final Planning Meeting (FPM)
A meeting that serves as the formal end of the exercise planning process. It is held to finalize exercise documentation and logistics.
Element | Considerations and Activities
Meeting Focus | Should be conducted for all exercises to ensure that all elements of the exercise are ready for conduct. Prior to the FPM, the planning team receives final drafts of all exercise materials. No major changes to the exercise's design, scope, or supporting documentation should take place at or following the FPM.
Discussion Points | • Conduct a comprehensive final review • Approve all remaining draft documents (for example, SitMan, MSEL, C/E Handbook) and presentation materials • Resolve any open planning issues and identify last-minute concerns • Review all exercise logistical activities (for example, schedule, registration, attire, special needs) • Re-engage with senior leaders to ensure alignment with guidance and intent
Exercise Tools | • Agenda materials • Briefing for presenting an overview of the exercise and meeting discussion points • Previous meeting minutes from the IPM, the MPM, and the MSEL if needed • All draft exercise documents and documentation • Previously finalized documents
Exercise Outcomes | • Final approval of exercise documents and material for production • Identified issues resolved • Attendees understand and approve exercise processes and procedures • Task assignments and logistical elements, including facilities, equipment, and schedules, are confirmed
Follow-up | • Finalize all publications • Prepare all supporting materials • Rehearse presentation and briefings • Prepare to conduct the exercise • Disseminate documentation and any additional instructions to all appropriate personnel prior to the exercise

## Exercise Types
Exercise Types
Discussion-Based Exercises:
Discussion-based exercises include seminars, workshops, tabletop exercises (TTXs), and games. These types of exercises familiarize players with or develop new plans, policies, procedures, and agreements. Discussion-based exercises focus on strategic, policy-oriented issues, and facilitators or presenters lead the discussion, keeping participants moving towards meeting the exercise objectives. The following tables provide the important information for each type of discussion-based exercise:
Discussion-Based Exercise Type: Seminar
A discussion-based exercise that orients participants to or provides an overview of authorities, strategies, plans, policies, procedures, protocols, resources, concepts, and ideas.
Element | Considerations and Activities
Purpose | • Provide a common framework of understanding • Provide a good starting point for developing or making major changes to existing plans, policies, or procedures
Structure | • Usually in the form of multiple presentations, Subject Matter Expert (SME) panels, or case study discussions • Lecture-based • Led by a seminar facilitator/presenter • Limited feedback or interaction from participants
Participant Goals | • Gain awareness of or assess interagency capabilities or inter-jurisdictional operations • Set objectives for future capabilities
Conduct Characteristics | • Minimal time constraints • Effective for small or large groups
Outcomes | • A report that captures the discussion, issues raised, and (if appropriate) action items that will address these issues • An After Action Report (AAR)/Improvement Plan (IP)
Discussion-Based Exercise Type: Workshop
A discussion-based exercise often employed to develop policy, plans, and procedures.
Element | Considerations and Activities
Purpose | • Increased participant interaction with a focus on achieving or building a product • Should have clearly defined objectives, products, or goals, and focus on a specific issue
Structure | • A group of individuals in a venue conducive to discussion • Lectures, presentations, panel or case study discussions, or decision support tools • Facilitated working breakout sessions • Led by a workshop facilitator/presenter
Participant Goals | • Develop a product as a group • Obtain consensus • Collect or share information
Conduct Characteristics | • Effective for small and large groups • Broad attendance by relevant stakeholders • Conducted based on clear objectives/goals • More participant discussion than lecture-based • Frequently uses breakout sessions to explore parts of an issue with similar groups
Outcomes | • Emergency Operations Plans • Mutual Aid Agreements • Standard Operation Procedures • Continuity of Operations Plans • Workshop Summary Report • An After-Actions Report (AAR)/Improvement Plan (IP)
Discussion-Based Exercise Type: Tabletop Exercise
A discussion-based exercise on response to a scenario, intended to generate a dialogue of various issues to facilitate a conceptual understanding, identify strengths and areas for improvement, and/or achieve changes in perceptions about plans, policies, or procedures.
Element | Considerations and Activities
Purpose | • Generate a discussion of various issues regarding an exercise scenario • Facilitate conceptual understanding, identify strengths and areas for improvement, and/or achieve changes in perceptions
Structure | • Scenario is presented to describe an event at a simulated time • Players apply their knowledge and skills to a list of problems presented by the facilitator • Problems are discussed as a group, and resolution may be reached and documented for later analysis • Breakout sessions • Discussion led by a facilitator • Presentation
Participant Goals | • Enhance general awareness • Enhance roles and responsibility understanding • Validate plans and procedures • Discuss concepts and/or assess types of systems in a defined incident
Conduct Characteristics | • Requires an experienced facilitator • In-depth discussion • Problem-solving environment • All participants should be encouraged to contribute to the discussion and be reminded that they are making decisions in a no-fault environment
Outcomes | • Recommended revisions to current plans, policies, or procedures • An After-Action Report (AAR)/Improvement Plan (IP)
Discussion-Based Exercise Type: Game
A discussion-based exercise that is a structured form of play designed for individuals or teams in a competitive or noncompetitive environment. It is an event players take part in and are guided by clear rules, data, and procedures for its execution. Games are designed to depict an actual or hypothetical situation to ensure that the participants make decisions ant take actions that would be plausible. Games can be used to reinforce training, stimulate team-building, or enhance operational and tactical capabilities.
Element | Considerations and Activities
Purpose | • Simulation of operations that explore the consequences of player decisions and actions • Identification of critical decision-making points is a major factor in the success of evaluating a game
Structure | • Usually in a environment that can involve two or more teams, using rules, data, and procedures designed to depict an actual or hypothetical situation • Decision-making may be either slow and deliberate or rapid and more stressful, depending on the exercise design and objectives • The open, decision-based format of a game can incorporate "what if" questions that expand exercise benefits • Depending on the game's design, the consequences of player actions can be either pre-scripted or decided dynamically
Participant Goals | • Explore decision-making processes and consequences • Conduct "what-if" analyses of existing plans • Evaluate existing and potential strategies
Conduct Characteristics | • No actual resources used • Often involves two or more teams • May include models and simulations of increasing complexity as the game progresses • May or may not include pre-scripted activities
Outcomes | • Validate plans, policies, and procedures or evaluating resource requirements • An After-Action Report (AAR)/Improvement Plan (IP)
Exercise Types
Operations-Based Exercises:
Operations-based exercises include drills, functional exercises (FE), and full-scale exercises (FSE). These exercises validate plans, policies, procedures, and agreements; clarify roles and responsibilities; and identify resource gaps. Operations-based exercises include a real-time response, such as initiating communications or mobilizing personnel and resources. The following tables provide important information for each type of operations-based exercise:
Operations-Based Exercise Type: Drill
An operations-based exercise often employed to validate a single operation or function.
Element | Considerations and Activities
Purpose | • Coordinated, supervised activity to validate a specific function or capability in a single agency/organization, often employed to validate a single operation or function • Validate procedures or practices and maintain current skills
Structure | • Can be standalone or used as a series of drills • Clearly defined plans, policies, procedures, and protocols need to be in place
Participant Goals | • Evaluate new plan, policies, or procedures • Practice and maintain skills • Prepare for future exercises
Conduct Characteristics | • Immediate feedback • Realistic environment • Narrow focus • Performance in isolation • Results are measured against established standards
Outcomes | • Determine if plans can be executed as designed • Assess whether more training is required • Reinforce best practices • An After-Action Report (AAR)/ Improvement Plan (IP)
Operations-Based Exercise Type: Functional Exercise
An operations-based exercise designed to test and evaluate capabilities and functions while in a realistic, real-time environment; however, movement of resources is usually simulated.
Element | Considerations and Activities
Purpose | • Validate and evaluate capabilities, multiple functions, and/or sub-functions, or interdependent groups of activities • Exercise plans, policies, procedures, and staff involved in management, direction, command, and control functions • Apply established plans, policies, and procedures under crisis conditions
Structure | • Events are projected through a realistic exercise scenario with event updates that drive activity typically at the management level • Controllers typically use a Master Scenario Events List (MSEL) to ensure participant activity remains within predefined boundaries • Evaluators observe behaviors and compare them against established plans, policies, procedures, and standard practices (if applicable)
Participant Goals | • Validate and evaluate capabilities • Focused on plans, policies, and procedures
Conduct Characteristics | • Conducted in a realistic environment • Usually simulated deployment of resources and personnel • Use of Simulation Cell and MSEL • Simulators can inject scenario elements
Outcomes | • Management evaluation of Emergency Operations Center (EOCs), command post, headquarters, and staff • Performance analysis • Cooperative relationships are strengthened • An After-Action Report (AAR)/Improvement Plan (IP)
Operations-Based Exercise Type: Full-Scale Exercise
An operations-based exercise that is typically the most complex and resource-intensive of the exercise types and often involves multiple agencies, jurisdictions/organizations, and real-time movement of resources.
Element | Considerations and Activities
Purpose | • Often includes many players operating under cooperative systems such as the Incident Command System (ICS), Unified Command • Focus on implementing and analyzing the plans, policies, and procedures that may have been developed in discussion-based exercises and honed during previous, smaller exercises
Structure | • Events are projected through an exercise scenario with event updates that drive activity at the operational level • Involves multiple agencies, organizations, and jurisdictions • Use of an MSEL drives player actions • SimCell controllers inject scenario elements • The level of support needed may be greater than that needed for other types of exercises • Conducted in a realistic environment to mirror a real incident by presenting complex problems
Participant Goals | • Demonstrate roles and responsibilities as addressed in plans, policies and procedures • Coordinate between multiple agencies, organizations, and jurisdictions
Conduct Characteristics | • Rapid problem solving: critical thinking • Mobilization of personnel and resources • Exercise site is usually large with many activities occurring simultaneously •Safety issues, particularly regarding the use of props and special effects, must be monitored • Demonstrate roles and responsibilities as addressed in plans, policies, and procedures
Outcomes | • Validate plans, policies, and procedures • Evaluate resource requirements • An After-Action Report (AAR)/Improvement Plan (IP)

## Core Capabilities
Mission Areas
Below is a table containing a list of the Mission Areas determined by FEMA along with the description. The mission areas are listed on the left and are defined on the right. This list is current as of July 2020.
Mission Areas |  | Description
Prevention |  | Prevent, avoid or stop an imminent, threatened, or actual act of terrorism.
Protection |  | Protect our citizens, residents, visitors, and assets against the greatest threats and hazards in a manner that allows our interests, aspirations, and way of life to thrive.
Mitigation |  | Reduce the loss of life and property by lessening the impact of future disasters.
Response |  | Respond quickly to save lives, protect property and the environment, and meet basic human needs in the aftermath of a catastrophic incident.
Recovery |  | Recover through a focus on the timely restoration, strengthening and revitalization of infrastructure, housing and a sustainable economy, as well as the health, social, cultural, historic, and environmental fabric of communities affected by a catastrophic incident.
Core Capabilities
Below is a table containing a list of the Core Capabilities determined by FEMA along with their Mission Area and description. The Mission Area and definition for each Core Capability is listed to the right. You can select the arrow at the top right to filter by mission area. This list is current as of July 2020.
Core Capabilities | Mission Area(s) | Description
Operational Coordination | All | Establish and maintain a unified and coordinated operational structure and process that appropriately integrates all critical stakeholders and supports the execution of core capabilities.
Planning | All | Conduct a systematic process engaging the whole community as appropriate in the development of executable strategic, operational, and/or tactical-level approaches to meet defined objectives.
Public Information and Warning | All | Deliver coordinated, prompt, reliable, and actionable information to the whole community through the use of clear, consistent, accessible, and culturally and linguistically appropriate methods to effectively relay information regarding any threat or hazard, as well as the actions being taken and the assistance being made available, as appropriate.
Community Resilience | Mitigation | Enable the recognition, understanding, communication of, and planning for risk and empower individuals and communities to make informed risk management decisions necessary to adapt to, withstand, and quickly recover from future incidents.
Long-term Vulnerability Reduction | Mitigation | Build and sustain resilient systems, communities, and critical infrastructure and key resources lifelines so as to reduce their vulnerability to natural, technological, and human-caused threats and hazards by lessening the likelihood, severity, and duration of the adverse consequences.
Risk and Disaster Resilience Assessment | Mitigation | Assess risk and disaster resilience so that decision makers, responders, and community members can take informed action to reduce their entity's risk and increase their resilience.
Threats and Hazards Identification | Mitigation | Identify the threats and hazards that occur in the geographic area; determine the frequency and magnitude; and incorporate this into analysis and planning processes so as to clearly understand the needs of a community or entity.
Forensics and Attribution | Prevention | Conduct forensic analysis, and attribute terrorist acts (including the means and methods of terrorism) to their source, to include forensic analysis as well as attribution for an attack and for the preparation for an attack in an effort to prevent initial or follow-on acts and/or swiftly develop counter-options.
Intelligence and Information Sharing | Prevention, Protection | Provide timely, accurate, and actionable information resulting from the planning, direction, collection, exploitation, processing, analysis, production, dissemination, evaluation, and feedback of available information concerning physical and cyber threats to the United States, its people, property, or interests; the development, proliferation, or use of WMDs; or any other matter bearing on U.S. national or homeland security by local, state, tribal, territorial, federal, and other stakeholders. Information sharing is the ability to exchange intelligence, information, data, or knowledge among government or private sector entities, as appropriate.
Interdiction and Disruption | Prevention, Protection | Delay, divert, intercept, halt, apprehend, or secure threats and/or hazards.
Screening, Search, and Detection | Prevention, Protection | Identify, discover, or locate threats and/or hazards through active and passive surveillance and search procedures. This may include the use of systematic examinations and assessments, bio surveillance, sensor technologies, or physical investigation and intelligence.
Access Control & Identity Verification | Protection | Apply and support necessary physical, technological, and cyber measures to control admittance to critical locations and systems.
Cybersecurity | Protection | Protect (and if needed, restore) electronic communications systems, information, and services from damage, unauthorized use, and exploitation.
Physical Protective Measures | Protection | Implement and maintain risk-informed countermeasures and policies protecting people, borders, structures, materials, products, and systems associated with key operational activities and critical infrastructure sectors.
Risk Management for Protection Programs and Activities | Protection | Identify, assess, and prioritize risks to inform Protection activities, countermeasures, and investments.
Supply Chain Integrity and Security | Protection | Strengthen the security and resilience of the supply chain.
Economic Recovery | Recovery | Return economic and business activities (including food and agriculture) to a healthy state and develop new business and employment opportunities that result in an economically viable community.
Health and Social Services | Recovery | Restore and improve health and social services capabilities and networks to promote the resilience, independence, health (including behavioral health), and well-being of the whole community.
Housing | Recovery | Implement housing solutions that effectively support the needs of the whole community and contribute to its sustainability and resilience.
Natural and Cultural Resources | Recovery | Protect natural and cultural resources and historic properties through appropriate planning, mitigation, response, and recovery actions to preserve, conserve, rehabilitate, and restore them consistent with post-disaster community priorities and best practices and in compliance with applicable environmental and historic preservation laws and executive orders.
Environmental Response/Health and Safety | Response | Conduct appropriate measures to ensure the protection of the health and safety of the public and workers, as well as the environment, from all-hazards in support of responder operations and the affected communities.
Critical Transportation | Response | Provide transportation (including infrastructure access and accessible transportation services) for response priority objectives, including the evacuation of people and animals, and the delivery of vital response personnel, equipment, and services into the affected areas.
Fatality Management Services | Response | Provide fatality management services, including decedent remains recovery and victim identification, working with local, state, tribal, territorial, insular area, and federal authorities to provide mortuary processes, temporary storage or permanent internment solutions, sharing information with mass care services for the purpose of reunifying family members and caregivers with missing persons/remains, and providing counseling to the bereaved.
Fire Management and Suppression | Response | Provide structural, wildland, and specialized firefighting capabilities to manage and suppress fires of all types, kinds, and complexities while protecting the lives, property, and the environment in the affected area.
Logistics and Supply Chain Management | Response | Deliver essential commodities, equipment, and services in support of impacted communities and survivors, to include emergency power and fuel support, as well as the coordination of access to community staples. Synchronize logistics capabilities and enable the restoration of impacted supply chains.
Mass Care Services | Response | Provide life-sustaining and human services to the affected population, to include hydration, feeding, sheltering, temporary housing, evacuee support, reunification, and distribution of emergency supplies.
Mass Search and Rescue Operations | Response | Deliver traditional and atypical search and rescue capabilities, including personnel, services, animals, and assets to survivors in need, with the goal of saving the greatest number of endangered lives in the shortest time possible.
On-Scene Security, Protection, and Law Enforcement | Response | Ensure a safe and secure environment through law enforcement and related security and protection operations for people and communities located within affected areas and also for response personnel engaged in lifesaving and life-sustaining operations.
Operational Communications | Response | Ensure the capacity for timely communications in support of security, situational awareness, and operations by any and all means available, among and between affected communities in the impact area and all response forces.
Public Health, Healthcare, and Emergency Medical Services | Response | Provide lifesaving medical treatment via Emergency Medical Services and related operations and avoid additional disease and injury by providing targeted public health, medical, and behavioral health support and products to all affected populations.
Situational Assessment | Response | Provide all decision makers with decision-relevant information regarding the nature and extent of the hazard, any cascading effects, and the status of the response.
Infrastructure Systems | Response, Recovery | Stabilize critical infrastructure functions, minimize health and safety threats, and efficiently restore and revitalize systems and services to support a viable, resilient community.

## Notification Form
Exercise Notification Form
OVERVIEW
Exercise Name:
Exercise Overview:
Mission Areas: |  |  | 1 | 2 |  | 3
Core Capabilities:
Mission Areas: |  |  | 4 | 5 |  | 6
Core Capabilities:
Primary Lead Planning Organization:
Exercise POC:
Type:
Primary Location:
Date: |  | Time: |  |  |  | Invitation Only
EXERCISE THREAT/HAZARD
THREAT |  | if OTHER is selected, enter description below
PLANNING MEETINGS
| Concept and Objectives Meeting (C&O) |  |  |  | Date:
| Initial Planning Meeting (IPC) |  |  |  | Date:
| Midterm Planning Meeting (MPM) |  |  |  | Date:
| Final Planning Meeting (FPM) |  |  |  | Date:
LEAD PLANNER:
PLANNING TEAM:

## Exercise Overview
Exercise Overview
Exercise Name:
Exercise Dates: | Start: | 0 |  | End:
Scope: | This is a planned for 1/0/1900 at
Exercise play is limited to the exercise participants.
The first draft of this AAR/IP is due no later than 02/14/1900.
The final draft of this AAR/IP is due no later than 03/30/1900.
Mission Area(s): | 1 |  | 2 |  | 3
Core Capabilities:
Mission Area(s): | 4 |  | 5 |  | 6
Core Capabilities:
Objective 1:
Objective 2:
Objective 3:
Objective 4:
Objective 5:
Objective 6:
Threat or Hazard:
Scenario:
Primary Lead Planning Organization:
Participating Organizations:
Exercise POC:
Contact Info:

## Meeting Sign-In Sheet
**FOUO** | Exercise Meeting Sign-in Roster |  |  |  |  | **FOUO**
Primary Lead Planning Organization |  | Exercise Name: |  | Exercise Meeting Type: |  |  | Date:
Organization | Printed Name |  | Signature |  | Email
*** Please Print Legibly. If we can't read it, you will not get credit for the exercise. ***
**FOUO** | Exercise Meeting Sign-in Roster |  |  |  |  | **FOUO**
Primary Lead Planning Organization |  | Exercise Name: |  | Exercise Meeting Type: |  |  | Date: | 01/00/1900
Organization | Printed Name |  | Signature |  | Email
*** Please Print Legibly. If we can't read it, you will not get credit for the exercise. ***

## EEG 1
EXERCISE EVALUATION GUIDE
Exercise Name: |  | Primary Lead Planning Organization:
Date: | 0 | Primary Location:
References:
Exercise Objective: | 1.
Core Capability: | 1.
#N/A
FINAL CORE CAPABILITY RATING:
Evaluator Name:
Rating Keys
Evaluator Email: |  |  | P | Perfomed without challenges (4 Points)
|  |  | S | Performed with some challenges (3 Points)
|  |  | M | Performed with major challenges (2 Points)
|  |  | U | Unable to be perfomed (1 Point)
Capabiliy Target #1
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements) |  |  |  |  | P
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #2
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #3
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #4
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #5
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capability Target #6
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed

## EEG 2
EXERCISE EVALUATION GUIDE
Exercise Name: |  | Primary Lead Planning Organization:
Date: | 0 | Primary Location:
References:
Exercise Objective: | 2.
Core Capability: | 2.
#N/A
FINAL CORE CAPABILITY RATING:
Evaluator Name:
Rating Keys
Evaluator Email: |  |  | P | Perfomed without challenges (4 Points)
|  |  | S | Performed with some challenges (3 Points)
|  |  | M | Performed with major challenges (2 Points)
|  |  | U | Unable to be perfomed (1 Point)
Capabiliy Target #1
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #2
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #3
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #4
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #5
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capability Target #6
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed

## EEG 3
EXERCISE EVALUATION GUIDE
Exercise Name: |  | Primary Lead Planning Organization:
Date: | 0 | Primary Location:
References:
Exercise Objective: | 3.
Core Capability: | 3.
#N/A
FINAL CORE CAPABILITY RATING:
Evaluator Name:
Rating Keys
Evaluator Email: |  |  | P | Perfomed without challenges (4 Points)
|  |  | S | Performed with some challenges (3 Points)
|  |  | M | Performed with major challenges (2 Points)
|  |  | U | Unable to be perfomed (1 Point)
Capabiliy Target #1
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #2
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #3
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #4
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #5
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capability Target #6
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed

## EEG 4
EXERCISE EVALUATION GUIDE
Exercise Name: |  | Primary Lead Planning Organization:
Date: | 0 | Primary Location:
References:
Exercise Objective: | 4.
Core Capability: | 4.
#N/A
FINAL CORE CAPABILITY RATING:
Evaluator Name:
Rating Keys
Evaluator Email: |  |  | P | Perfomed without challenges (4 Points)
|  |  | S | Performed with some challenges (3 Points)
|  |  | M | Performed with major challenges (2 Points)
|  |  | U | Unable to be perfomed (1 Point)
Capabiliy Target #1
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #2
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #3
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #4
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #5
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capability Target #6
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed

## EEG 5
EXERCISE EVALUATION GUIDE
Exercise Name: |  | Primary Lead Planning Organization:
Date: | 0 | Primary Location:
References:
Exercise Objective: | 5.
Core Capability: | 5.
#N/A
FINAL CORE CAPABILITY RATING:
Evaluator Name:
Rating Keys
Evaluator Email: |  |  | P | Perfomed without challenges (4 Points)
|  |  | S | Performed with some challenges (3 Points)
|  |  | M | Performed with major challenges (2 Points)
|  |  | U | Unable to be perfomed (1 Point)
Capabiliy Target #1
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #2
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #3
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #4
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #5
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capability Target #6
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed

## EEG 6
EXERCISE EVALUATION GUIDE
Exercise Name: |  | Primary Lead Planning Organization:
Date: | 0 | Primary Location:
References:
Exercise Objective: | 6.
Core Capability: | 6.
#N/A
FINAL CORE CAPABILITY RATING:
Evaluator Name:
Rating Keys
Evaluator Email: |  |  | P | Perfomed without challenges (4 Points)
|  |  | S | Performed with some challenges (3 Points)
|  |  | M | Performed with major challenges (2 Points)
|  |  | U | Unable to be perfomed (1 Point)
Capabiliy Target #1
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #2
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #3
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #4
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capabiliy Target #5
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed
Capability Target #6
Critical Task #1: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #2: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #3: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #4: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #5: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #6: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #7: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #8: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #9: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
Critical Task #10: |  |  |  |  | Rating
Observations, Comments, and Notes (Strengths/Areas for Improvements)
ORGANIZATIONAL CAPABILITY TARGET RATING:
Capability Target Strengths Observed

## MSEL
Event #: | Time: | Event Type: | Inject Mode: | From: | To: | Inject Message/Question | Expected Action: | POC/Author: | Core Capability: | Comment:

## Analysis of Core Capabilities 1
Analysis of Core Capabilities
Aligning exercise objectives and core capabilities provides a consistent taxonomy for evaluation that transcends individual exercises to support preparedness reporting and trend analysis. Table 1 includes the exercise objectives, aligned core capabilities, and performance ratings for each core capability as observed during the exercise and determined by the evaluation team.
Objectives | Core Capabilities | Results
1.
2.
3.
4.
5.
6.
Ratings Definitions:
• Performed without Challenges (P): The targets and critical tasks associated with the core capability were completed in a manner that achieved the objective(s) and did not negatively impact the performance of other activities. Performance of this activity did not contribute to additional health and/or safety risks for the public or for emergency workers, and it was conducted in accordance with applicable plans, policies, procedures, regulations, and laws. • Performed with Some Challenges (S): The targets and critical tasks associated with the core capability were completed in a manner that achieved the objective(s) and did not negatively impact the performance of other activities. Performance of this activity did not contribute to additional health and/or safety risks for the public or for emergency workers, and it was conducted in accordance with applicable plans, policies, procedures, regulations, and laws. However, opportunities to enhance effectiveness and/or efficiency were identified. • Performed with Major Challenges (M): The targets and critical tasks associated with the core capability were completed in a manner that achieved the objective(s), but some or all of the following were observed: demonstrated performance had a negative impact on the performance of other activities; contributed to additional health and/or safety risks for the public or for emergency workers; and/or was not conducted in accordance with applicable plans, policies, procedures, regulations, and laws. • Unable to Perform (U): The targets and critical tasks associated with the core capability were not performed in a manner that achieved the objective(s).
The following sections provide an overview of the performance related to each exercise objective and associated core capability, highlighting strengths and areas for improvement.
Obj 1
Performed without challenges (P)
Performed with some challenges(S)
Performed with major challenges (M)
Unable to perform (U)
Obj 2
Performed without challenges (P)
Performed with some challenges(S)
Performed with major challenges (M)
Unable to perform (U)
Not Applicable
Obj 3
Performed without challenges (P)
Performed with some challenges(S)
Performed with major challenges (M)
Unable to perform (U)
Not Applicable
Obj 4
Performed without challenges (P)
Performed with some challenges(S)
Performed with major challenges (M)
Unable to perform (U)
Not Applicable
Obj 5
Performed without challenges (P)
Performed with some challenges(S)
Performed with major challenges (M)
Unable to perform (U)
Not Applicable
Obj 6
Performed without challenges (P)
Performed with some challenges(S)
Performed with major challenges (M)
Unable to perform (U)
Not Applicable
Not Applicable

## Analysis of Core Capabilities 2
ANALYSIS OF CORE CAPABILITIES CONTINUED
1.
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Objective 1:
Capability Level:
The capability level assigned to objective one can be attributed to the following strengths and areas for improvement. *If no areas for improvement were identified, the objective is assigned a full capability level. *If any areas for improvement were identified, the objective is assigned a partial capability level.
Strengths
The following strengths were identified during the exercise:
Strength 1:
Strength 2:
Strength 3:
Areas For Improvement (AFI)
The following areas require improvement in order for objective one to achieve a full capability level:
AFI 1:
AFI 2:
AFI 3:
AFI 4:
AFI 5:
Analyses
The following analyses explain how each AFI prevented the objective from being met (this statement should not include any solutions or corrective actions):
Analysis 1:
Analysis 2:
Analysis 3:
Analysis 4:
Analysis 5:
Reference
The following reference(s) was used in the planning and development of this exercise and can be referred to as a source for further information regarding objective one.
Reference:
2.
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Objective 2:
Capability Level:
The capability level assigned to objective two can be attributed to the following strengths and areas for improvement. *If no areas for improvement were identified, the objective is assigned a full capability level. *If any areas for improvement were identified, the objective is assigned a partial capability level.
Strengths
The following strengths were identified during the exercise:
Strength 1:
Strength 2:
Strength 3:
Areas For Improvement (AFI)
The following areas require improvement in order for objective two to achieve a full capability level:
AFI 1:
AFI 2:
AFI 3:
AFI 4:
AFI 5:
Analyses
The following analyses explain how each AFI prevented the objective from being met (this statement should not include any solutions or corrective actions):
Analysis 1:
Analysis 2:
Analysis 3:
Analysis 4:
Analysis 5:
Reference
The following reference(s) was used in the planning and development of this exercise and can be referred to as a source for further information regarding objective two.
Reference:
3.
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Objective 3:
Capability Level:
The capability level assigned to objective three can be attributed to the following strengths and areas for improvement. *If no areas for improvement were identified, the objective is assigned a full capability level. *If any areas for improvement were identified, the objective is assigned a partial capability level.
Strengths
The following strengths were identified during the exercise:
Strength 1:
Strength 2:
Strength 3:
Areas For Improvement (AFI)
The following areas require improvement in order for objective three to achieve a full capability level:
AFI 1:
AFI 2:
AFI 3:
AFI 4:
AFI 5:
Analyses
The following analyses explain how each AFI prevented the objective from being met (this statement should not include any solutions or corrective actions):
Analysis 1:
Analysis 2:
Analysis 3:
Analysis 4:
Analysis 5:
Reference
The following reference(s) was used in the planning and development of this exercise and can be referred to as a source for further information regarding objective three.
Reference:
4.
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Objective 4:
Capability Level:
The capability level assigned to objective four can be attributed to the following strengths and areas for improvement. *If no areas for improvement were identified, the objective is assigned a full capability level. *If any areas for improvement were identified, the objective is assigned a partial capability level.
Strengths
The following strengths were identified during the exercise:
Strength 1:
Strength 2:
Strength 3:
Areas For Improvement (AFI)
The following areas require improvement in order for objective four to achieve a full capability level:
AFI 1:
AFI 2:
AFI 3:
AFI 4:
AFI 5:
Analyses
The following analyses explain how each AFI prevented the objective from being met (this statement should not include any solutions or corrective actions):
Analysis 1:
Analysis 2:
Analysis 3:
Analysis 4:
Analysis 5:
Reference
The following reference(s) was used in the planning and development of this exercise and can be referred to as a source for further information regarding objective four.
Reference:
5.
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Objective 5:
Capability Level:
The capability level assigned to objective five can be attributed to the following strengths and areas for improvement. *If no areas for improvement were identified, the objective is assigned a full capability level. *If any areas for improvement were identified, the objective is assigned a partial capability level.
Strengths
The following strengths were identified during the exercise:
Strength 1:
Strength 2:
Strength 3:
Areas For Improvement (AFI)
The following areas require improvement in order for objective five to achieve a full capability level:
AFI 1:
AFI 2:
AFI 3:
AFI 4:
AFI 5:
Analyses
The following analyses explain how each AFI prevented the objective from being met (this statement should not include any solutions or corrective actions):
Analysis 1:
Analysis 2:
Analysis 3:
Analysis 4:
Analysis 5:
Reference
The following reference(s) was used in the planning and development of this exercise and can be referred to as a source for further information regarding objective five.
Reference:
6.
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Objective 6:
Capability Level:
The capability level assigned to objective six can be attributed to the following strengths and areas for improvement. *If no areas for improvement were identified, the objective is assigned a full capability level. *If any areas for improvement were identified, the objective is assigned a partial capability level.
Strengths
The following strengths were identified during the exercise:
Strength 1:
Strength 2:
Strength 3:
Areas For Improvement (AFI)
The following areas require improvement in order for objective six to achieve a full capability level:
AFI 1:
AFI 2:
AFI 3:
AFI 4:
AFI 5:
Analyses
The following analyses explain how each AFI prevented the objective from being met (this statement should not include any solutions or corrective actions):
Analysis 1:
Analysis 2:
Analysis 3:
Analysis 4:
Analysis 5:
Reference
The following reference(s) was used in the planning and development of this exercise and can be referred to as a source for further information regarding objective six.
Reference:

## Appendix A-IP
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise Conducted on 01/00/1900
Core Capability | Issue/Area for Improvement | Corrective Action | Capability Element | Primary Responsible Organization | Organization POC | Start Date | Projected Completion Date
1.
Core Capability | Issue/Area for Improvement | Corrective Action | Capability Element | Primary Responsible Organization | Organization POC | Start Date | Projected Completion Date
2.
Core Capability | Issue/Area for Improvement | Corrective Action | Capability Element | Primary Responsible Organization | Organization POC | Start Date | Projected Completion Date
3.
Core Capability | Issue/Area for Improvement | Corrective Action | Capability Element | Primary Responsible Organization | Organization POC | Start Date | Projected Completion Date
4.
Core Capability | Issue/Area for Improvement | Corrective Action | Capability Element | Primary Responsible Organization | Organization POC | Start Date | Projected Completion Date
5.
Core Capability | Issue/Area for Improvement | Corrective Action | Capability Element | Primary Responsible Organization | Organization POC | Start Date | Projected Completion Date
6.
Element 1-1
Planning
Organization
Equipment
Training
Exercise
Element 1-2
Planning
Organization
Equipment
Training
Exercise
Element 1-3
Planning
Organization
Equipment
Training
Exercise
Element 1-4
Planning
Organization
Equipment
Training
Exercise
Element 1-5
Planning
Organization
Equipment
Training
Exercise
Element 2-1
Planning
Organization
Equipment
Training
Exercise
Element 3-1
Planning
Organization
Equipment
Training
Exercise
Element 4-1
Planning
Organization
Equipment
Training
Exercise
Element 5-1
Planning
Organization
Equipment
Training
Exercise
Element 6-1
Planning
Organization
Equipment
Training
Exercise
Element 6-2
Planning
Organization
Equipment
Training
Exercise
Element 6-3
Planning
Organization
Equipment
Training
Exercise
Element 6-4
Planning
Organization
Equipment
Training
Exercise
Element 6-5
Planning
Organization
Equipment
Training
Exercise
Element 5-2
Planning
Organization
Equipment
Training
Exercise
Element 5-3
Planning
Organization
Equipment
Training
Exercise
Element 5-4
Planning
Organization
Equipment
Training
Exercise
Element 5-5
Planning
Organization
Equipment
Training
Exercise
Element 4-2
Planning
Organization
Equipment
Training
Exercise
Element 4-3
Planning
Organization
Equipment
Training
Exercise
Element 4-4
Planning
Organization
Equipment
Training
Exercise
Element 4-5
Planning
Organization
Equipment
Training
Exercise
Element 3-2
Planning
Organization
Equipment
Training
Exercise
Element 3-3
Planning
Organization
Equipment
Training
Exercise
Element 3-4
Planning
Organization
Equipment
Training
Exercise
Element 3-5
Planning
Organization
Equipment
Training
Exercise
Element 2-2
Planning
Organization
Equipment
Training
Exercise
Element 2-3
Planning
Organization
Equipment
Training
Exercise
Element 2-4
Planning
Organization
Equipment
Training
Exercise
Element 2-5
Planning
Organization
Equipment
Training
Exercise

## Ex Sign-In Sheet
**FOUO** | Exercise Sign-in Roster |  |  |  |  | **FOUO**
Primary Lead Planning Organization |  | Exercise Name: |  | Exercise Type: |  |  | Date: | 0
Organization | Printed Name |  | Signature |  | Email
*** Please Print Legibly. If we can't read it, you will not get credit for the exercise. ***
**FOUO** | Exercise Sign-in Roster |  |  |  |  | **FOUO**
Primary Lead Planning Organization |  | Exercise Name: |  | Exercise Type: |  |  | Date: | 0
Organization | Printed Name |  | Signature |  | Email
*** Please Print Legibly. If we can't read it, you will not get credit for the exercise. ***

## AAR
Exercise Overview
Exercise Name:
Exercise Dates: | 0
Scope: | This is a planned for 1/0/1900 at
Exercise play is limited to the exercise participants.
Mission Areas:
Core Capapbities:
Mission Areas:
Core Capapbities:
Objectives:
Threat/Hazard:
Scenario:
Sponsor:
Participating Organizations:
Point of Contact: | at
Analysis of Core Capabilities
Aligning exercise objectives and core capabilities provides a consistent taxonomy for evaluation that transends individual exercises to support preparedness reporting and trend analysis. Table 1 includes the exercise objectives aligned core capabilities, and performance raings for each core capability as observed during the exercise and determined by the evaluaion team.
Objectives |  |  | Core Capabilities |  | Results
1.
2.
3.
4.
5.
6.
Rating Definitions:
• Performed without Challenges (P): The target and critical tasks associated with the core capability were completed in a manner that achieved the objective(s) and did not negatively impact the performance of other activities. Performance of this activity did not contribute to additional health and/or safety risks for the public or for emergency workers, and it was conducted in accordance with applicable plans, policies, procedures, regulations, and laws. •Performed with Some Challenges (S): The targets and critical tasks associated with the core capability were completed in a manner that achieved the objective(s) and did not negatively impact the performance of other activities. Performance of this activity did not contribute to additional health and/or safety risks for the public or for emergency workers, and it was conducted in accordance with applicable plans, policies, procedures, regulations, and laws. However, opportunitites to enhance effectiveness and /or efficiency were identified. •Performed with Major Challenges (M): The targets and critical tasks associated with the core capability were completed in a manner that achieved the objective(s), but some or all of the following were observed: demonstrated performance had a negative impact on the performance of other activities; contributed to additional health and/or safety risks for the public or for emergency workers; and/or was not conducted in accordance with applicable plans, policies, procedures, regulations, and laws. •Unable to be Performed (U): The targets and critical tasks associated with the core capability were not performed in a manner that achieved the objective(s).
Analysis of Objective #1
Purpose: | This is an analysis of exercise performance as related to the objective and its associated core capability, highlighting strengths and identifying areas for improvement.
Objective #1:
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Strengths
The following strengths were identified during the exercise:
#1.
#2.
#3.
Areas For Improvement
The following areas require improvement to achieve a Full Capability Level.
#1.
#2.
#3.
#4.
#5.
Analyses
#1:
#2:
#3:
#4:
#5:
Reference
Reference:
Analysis of Objective #2
Purpose: | This is an analysis of exercise performance as related to the objective and its associated core capability, highlighting strengths and identifying areas for improvement.
Objective #2:
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Strengths
The following strengths were identified during the exercise:
#1.
#2.
#3.
Areas For Improvement
The following areas require improvement to achieve a Full Capability Level.
#1.
#2.
#3.
#4.
#5.
Analyses
#1:
#2:
#3:
#4:
#5:
Reference
Reference:
Analysis of Objective #3
Purpose: | This is an analysis of exercise performance as related to the objective and its associated core capability, highlighting strengths and identifying areas for improvement.
Objective #3:
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Strengths
The following strengths were identified during the exercise:
#1.
#2.
#3.
Areas For Improvement
The following areas require improvement to achieve a Full Capability Level.
#1.
#2.
#3.
#4.
#5.
Analyses
#1:
#2:
#3:
#4:
#5:
Reference
Reference:
Analysis of Objective #4
Purpose: | This is an analysis of exercise performance as related to the objective and its associated core capability, highlighting strengths and identifying areas for improvement.
Objective #4:
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Strengths
The following strengths were identified during the exercise:
#1.
#2.
#3.
Areas For Improvement
The following areas require improvement to achieve a Full Capability Level.
#1.
#2.
#3.
#4.
#5.
Analyses
#1:
#2:
#3:
#4:
#5:
Reference
Reference:
Analyses of Objective #5
Purpose: | This is an analysis of exercise performance as related to the objective and its associated core capability, highlighting strengths and identifying areas for improvement.
Objective #5:
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Strengths
The following strengths were identified during the exercise:
#1.
#2.
#3.
Areas For Improvement
The following areas require improvement to achieve a Full Capability Level.
#1.
#2.
#3.
#4.
#5.
Analyses
#1:
#2:
#3:
#4:
#5:
Reference
Reference:
Analysis of Objective #6
Purpose: | This is an analysis of exercise performance as related to the objective and its associated core capability, highlighting strengths and identifying areas for improvement.
Objective #6:
The strengths and areas for improvement for each objective aligned to this core capability are described below.
Strengths
The following strengths were identified during the exercise:
#1.
#2.
#3.
Areas For Improvement
The following areas require improvement to achieve a Full Capability Level.
#1.
#2.
#3.
#4.
#5.
Analyses
#1:
#2:
#3:
#4:
#5:
Reference
Reference:
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise . Conducted on 01/00/00.
Core Capability #1.
Issue/Areas For Improvement | Corrective Action | Capability Element | Start Date | Comp. Date | Responsible Organization & Point of Contact
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise . Conducted on 01/00/00.
Core Capability #2.
Issue/Areas For Improvement | Corrective Action | Capability Element | Start Date | Comp. Date | Responsible Organization & Point of Contact
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise . Conducted on 01/00/00.
Core Capability #3.
Issue/Areas For Improvement | Corrective Action | Capability Element | Start Date | Comp. Date | Responsible Organization & Point of Contact
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise . Conducted on 01/00/00.
Core Capability #4.
Issue/Areas For Improvement | Corrective Action | Capability Element | Start Date | Comp. Date | Responsible Organization & Point of Contact
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise . Conducted on 01/00/00.
Core Capability #5.
Issue/Areas For Improvement | Corrective Action | Capability Element | Start Date | Comp. Date | Responsible Organization & Point of Contact
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
Appendix A: Improvement Plan
This IP has been developed for as a result of the exercise . Conducted on 01/00/00.
Core Capability #6.
Issue/Areas For Improvement | Corrective Action | Capability Element | Start Date | Comp. Date | Responsible Organization & Point of Contact
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /
|  | Planning |  |  | /

## ENUM (hidden)
Mission Areas | Prevention | Protection | Response | Mitigation | Recovery | Threats | Exercises | Rating Key | Access Control & Identity Verification | Apply and support necessary physical, technological, and cyber measures to control admittance to critical locations and systems. | Event Type: | Inject Mode: | 5 | 1 | 1 | 1 | 1 | 1 | 1 | Types of Exercise Meetings: | Core Capabilities
[9 empty] | Community Resilience | Enable the recognition, understanding, communication of, and planning for risk and empower individuals and communities to make informed risk management decisions necessary to adapt to, withstand, and quickly recover from future incidents. |  |  | 5 | 1 | 1 | 1 | 1 | 1 | 1
Prevention | Planning | Planning | Planning | Planning | Planning | Active Shooter | Seminar | P | Critical Transportation | Provide transportation (including infrastructure access and accessible transportation services) for response priority objectives, including the evacuation of people and animals, and the delivery of vital response personnel, equipment, and services into the affected areas. | Player Inject | In Person | 5 | 1 | 1 | 1 | 1 | 1 | 1 | Concept and Objectives Meeting (C&O) | Planning
Protection | Public Information and Warning | Public Information and Warning | Public Information and Warning | Public Information and Warning | Public Information and Warning | Aerosol Anthrax | Workshop | M | Cybersecurity | Protect (and if needed, restore) electronic communications systems, information, and services from damage, unauthorized use, and exploitation. | Contingency Inject | Radio | 5 | 1 | 1 | 1 | 1 | 1 | 1 | Initial Planning Meeting (IPM) | Public Information and Warning
Response | Operational Coordination | Operational Coordination | Operational Coordination | Operational Coordination | Operational Coordination | Blister Agent | Tabletop Exercise | S | Economic Recovery | Return economic and business activities (including food and agriculture) to a healthy state and develop new business and employment opportunities that result in an economically viable community. | Media Inject | Electronic Mail | 5 | 1 | 1 | 1 | 1 | 1 | 1 | C&O/IPM | Operational Coordination
Mitigation | Forensics and Attribution | Intelligence and Information Sharing | Critical Transportation | Community Resilience | Infrastructure Systems | Chlorine Tank Explosion | Game | U | Environmental Response/Health and Safety | Conduct appropriate measures to ensure the protection of the health and safety of the public and workers, as well as the environment, from all-hazards in support of responder operations and the affected communities. | Question | Fax | 5 | Appendix A-IP | [5 empty] | Midterm Planning Meeting (MPM) | Forensics and Attribution
Recovery | Intelligence and Information Sharing | Interdiction and Disruption | Environmental Response/Health and Safety | Long-term Vulnerability Reduction | Economic Recovery | Civil Unrest | Drill |  | Fatality Management Services | Provide fatality management services, including decedent remains recovery and victim identification, working with local, state, tribal, territorial, insular area, and federal authorities to provide mortuary processes, temporary storage or permanent internment solutions, sharing information with mass care services for the purpose of reunifying family members and caregivers with missing persons/remains, and providing counseling to the bereaved. | Other | Satellite Phone | [7 empty] | Master Scenario Events List Meeting (MSEL) | Intelligence and Information Sharing
| Interdiction and Disruption | Screening, Search, and Detection | Fatality Management Services | Risk and Disaster Resilience Assessment | Health and Social Services | Criminal Activity | Functional Exercise |  | Fire Management and Suppression | Provide structural, wildland, and specialized firefighting capabilities to manage and suppress fires of all types, kinds, and complexities while protecting the lives, property, and the environment in the affected area. |  | Social Media | Objective | Element 1 | Element 2 | Element 3 | Element 4 | Element 5 | Element 6 | Final Planning Meeting (FPM) | Interdiction and Disruption
| Screening, Search, and Detection | Access Control and Identity Verification | Fire Management and Suppression | Threats and Hazards Identification | Housing | Cyber | Full-Scale Exercise |  | Forensics and Attribution | Conduct forensic analysis and attribute terrorist acts (including the means and methods of terrorism) to their source, to include forensic analysis as well as attribution for an attack and for the preparation for an attack in an effort to prevent initial or follow-on acts and/or swiftly develop counter-options. |  | Other | Results | [6 empty] | Training | Screening, Search, and Detection
|  | Cybersecurity | Infrastructure Systems |  | Natural and Cultural Resources | Earthquake |  |  | Health and Social Services | Restore and improve health and social services capabilities and networks to promote the resilience, independence, health (including behavioral health), and well-being of the whole community. | [10 empty] | Access Control and Identity Verification
|  | Physical Protective Measures | Logistics and Supply Chain Management |  |  | Epidemic |  |  | Housing | Implement housing solutions that effectively support the needs of the whole community and contribute to its sustainability and resilience. | [10 empty] | Cybersecurity
|  | Risk Management for Protection Programs and Activities | Mass Care Services |  |  | Evacuation |  |  | Infrastructure Systems | Stabilize critical infrastructure functions, minimize health and safety threats, and efficiently restore and revitalize systems and services to support a viable, resilient community. | [10 empty] | Physical Protective Measures
|  | Supply Chain Integrity and Security | Mass Search and Rescue Operations |  |  | Fire |  |  | Intelligence and Information Sharing | Provide timely, accurate, and actionable information resulting from the planning, direction, collection, exploitation, processing, analysis, production, dissemination, evaluation, and feedback of available information concerning physical and cyber threats to the United States, its people, property, or interests; the development, proliferation, or use of WMDs; or any other matter bearing on U.S. national or homeland security by local, state, tribal, territorial, federal, and other stakeholders. Information sharing is the ability to exchange intelligence, information, data, or knowledge among government or private sector entities, as appropriate. | [10 empty] | Risk Management for Protection Programs and Activities
|  |  | On-Scene Security, Protection, and Law Enforcement |  |  | Flood |  |  | Interdiction and Disruption | Delay, divert, intercept, halt, apprehend, or secure threats and/or hazards. | [10 empty] | Supply Chain Integrity and Security
|  |  | Operational Communications |  |  | Food Contamination |  |  | Logistics and Supply Chain Management | Deliver essential commodities, equipment, and services in support of impacted communities and survivors, to include emergency power and fuel support, as well as the coordination of access to community staples. Synchronize logistics capabilities and enable the restoration of impacted supply chains. | [10 empty] | Critical Transportation
|  |  | Public Health, Healthcare, and Emergency Medical Services |  |  | Foreign Animal Disease |  |  | Long-term Vulnerability Reduction | Build and sustain resilient systems, communities, and critical infrastructure and key resources lifelines so as to reduce their vulnerability to natural, technological, and human-caused threats and hazards by lessening the likelihood, severity, and duration of the adverse consequences. | [10 empty] | Environmental Response/Health and Safety
|  |  | Situational Assessment |  |  | HazMat |  |  | Mass Care Services | Provide life-sustaining and human services to the affected population, to include hydration, feeding, sheltering, temporary housing, evacuee support, reunification, and distribution of emergency supplies. | [10 empty] | Fatality Management Services
[6 empty] | Hurricane |  |  | Mass Search and Rescue Operations | Deliver traditional and atypical search and rescue capabilities, including personnel, services, animals, and assets to survivors in need, with the goal of saving the greatest number of endangered lives in the shortest time possible. | [10 empty] | Fire Management and Suppression
[6 empty] | Ice Storm |  |  | Natural and Cultural Resources | Protect natural and cultural resources and historic properties through appropriate planning, mitigation, response, and recovery actions to preserve, conserve, rehabilitate, and restore them consistent with post-disaster community priorities and best practices and in compliance with applicable environmental and historic preservation laws and executive orders. | [10 empty] | Infrastructure Systems
[6 empty] | Improvised Explosive Device |  |  | On-Scene Security, Protection, and Law Enforcement | Ensure a safe and secure environment through law enforcement and related security and protection operations for people and communities located within affected areas and also for response personnel engaged in lifesaving and life-sustaining operations. | [10 empty] | Logistics and Supply Chain Management
[6 empty] | Mass Care |  |  | Operational Communications | Ensure the capacity for timely communications in support of security, situational awareness, and operations by any and all means available, among and between affected communities in the impact area and all response forces. | [10 empty] | Mass Care Services
[6 empty] | Mass Casualty |  |  | Operational Coordination | Establish and maintain a unified and coordinated operational structure and process that appropriately integrates all critical stakeholders and supports the execution of core capabilities. | [10 empty] | Mass Search and Rescue Operations
[6 empty] | Medical |  |  | Physical Protective Measures | Implement and maintain risk-informed countermeasures, and policies protecting people, borders, structures, materials, products, and systems associated with key operational activities and critical infrastructure sectors. | [10 empty] | On-Scene Security, Protection, and Law Enforcement
[6 empty] | Military Action |  |  | Planning | Conduct a systematic process engaging the whole community as appropriate in the development of executable strategic, operational, and/or tactical-level approaches to meet defined objectives. | [10 empty] | Operational Communications
[6 empty] | Natural |  |  | Public Health, Healthcare, and Emergency Medical Services | Provide lifesaving medical treatment via Emergency Medical Services and related operations and avoid additional disease and injury by providing targeted public health, medical, and behavioral health support, and products to all affected populations. | [10 empty] | Public Health, Healthcare, and Emergency Medical Services
[6 empty] | Nerve Agent |  |  | Public Information and Warning | Deliver coordinated, prompt, reliable, and actionable information to the whole community through the use of clear, consistent, accessible, and culturally and linguistically appropriate methods to effectively relay information regarding any threat or hazard, as well as the actions being taken and the assistance being made available, as appropriate. | [10 empty] | Situational Assessment
[6 empty] | Pandemic Influenza |  |  | Risk and Disaster Resilience Assessment | Assess risk and disaster resilience so that decision makers, responders, and community members can take informed action to reduce their entity's risk and increase their resilience. | [10 empty] | Community Resilience
[6 empty] | Plague |  |  | Risk Management for Protection Programs and Activities | Identify, assess, and prioritize risks to inform Protection activities, countermeasures, and investments. | [10 empty] | Long-term Vulnerability Reduction
[6 empty] | Radiological |  |  | Screening, Search, and Detection | Identify, discover, or locate threats and/or hazards through active and passive surveillance and search procedures. This may include the use of systematic examinations and assessments, bio surveillance, sensor technologies, or physical investigation and intelligence. | [10 empty] | Risk and Disaster Resilience Assessment
[6 empty] | Radiological Dispersal Device |  |  | Situational Assessment | Provide all decision makers with decision-relevant information regarding the nature and extent of the hazard, any cascading effects, and the status of the response. | [10 empty] | Threats and Hazards Identification
[6 empty] | Search & Rescue |  |  | Supply Chain Integrity and Security | Strengthen the security and resilience of the supply chain. | [10 empty] | Economic Recovery
[6 empty] | Severe Thunderstorm |  |  | Threats and Hazards Identification | Identify the threats and hazards that occur in the geographic area; determine the frequency and magnitude; and incorporate this into analysis and planning processes so as to clearly understand the needs of a community or entity. | [10 empty] | Health and Social Services
[6 empty] | Straight Line Winds | [14 empty] | Housing
[6 empty] | Technology | [14 empty] | Natural and Cultural Resources
Terrorist
Tornado
Toxic Industrial Chemical
Workplace Violence
Other: